## CUSTOMER ACCESS
TYPE OF REQUEST | PGE CONTACT | QC CONTACT | PROJECT DUE DATE | COUNTDOWN TO DUE DATE | INTERNAL REQ. DATE | APPT INFO FULL (AS SCHEDULED) | STATUS / DUE TIME | CLEAR | WORK GROUP | DATE PG&E PROVIDED | REQ. DATE | TYPE | CONFIRMATION # | VENDOR | STREET ADDRESS/ SEGMENT ID | CITY | DIVISION | *RC | CUSTOMER CONTACT INFO | REQUEST NOTES | EMAIL | PHONE 1 | ATTMPT 1 | ATTMPT 2 | ATTMPT 3 | 3 ATTEMPTS | DATE SENT BACK TO PG&E | APPT DATE | APPT TIME | Column29 | Column30 | Newline | MODIFIED (DATE) | STREET ADDRESS UPPER | CITY UPPER | Missed appoinment | MAP | Tomorrow | WORK ORDER # | Column42 | Column45 | FIELD SUBMISSION | Column3 | Column4 | Column5 | Column6 | Column38 | CC Notes | QC Notes | PG&E APPT REPORT | STREET NAME | OPERATOR | All info | ESTIMATED CLEANING TIME | CLEANING ACCESS POINT | CLEANING END POINT | CUSTOMER ACCESS DONE | Inspected
CUSTOMER ACCESS | ROBERTO ROMAN | SHISHIR 925.384.1196 | 2020-10-27 | 0 | 2020-10-27 10:27 |  |  |  | GC |  |  | POST | 35057374-R9R0-19380 | PROPIPE | 8380 HAMILTON WAY | Stockton | STOCKTON | 1 |  | NEED ACCESS TO PROPERTY TO CLEAR THE LATERAL TO CO | [10 empty] | - @DIVISION/CITY: STOCKTON / StocktonGC // POST 35057374-R9R0-193808380 HAMILTON WAY, StocktonCUSTOMER: NOTE: NEED ACCESS TO PROPERTY TO CLEAR THE LATERAL TO COQC: SHISHIR 925.384.1196DUE DATE: 10/27/20:: |  | 2020-10-27 10:27 | 8380 HAMILTON WAY | STOCKTON |  |  | 2020-10-28 | [11 empty] | - @StocktonCONFIRMATION: 35057374-R9R0-19380TYPE: POST8380 HAMILTON WAY, StocktonCUSTOMER: NOTE: NEED ACCESS TO PROPERTY TO CLEAR THE LATERAL TO CO
CUSTOMER ACCESS | ROBERTO ROMAN | SHISHIR 925.384.1196 | 2020-10-27 | 0 | 2020-10-26 12:50 |  | PENDING PG&E (CONTACT INFO) |  | GC |  | 2020-10-26 | POST | 35057374-R9R0-19380 | PROPIPE | 3002 MONTICELLO DR | Stockton | STOCKTON | 1 |  | Need CA to access Wall CO. Lower CO is buried |  | . | [8 empty] | - @DIVISION/CITY: STOCKTON / StocktonGC // POST 35057374-R9R0-193803002 MONTICELLO DR, StocktonCUSTOMER: NOTE: Need CA to access Wall CO. Lower CO is buriedQC: SHISHIR 925.384.1196DUE DATE: 10/27/20:: |  | 2020-10-27 10:27 | 3002 MONTICELLO DR | STOCKTON |  |  | 2020-10-28 | [11 empty] | - @StocktonCONFIRMATION: 35057374-R9R0-19380TYPE: POST3002 MONTICELLO DR, StocktonCUSTOMER: NOTE: Need CA to access Wall CO. Lower CO is buried
CUSTOMER ACCESS | ROBERTO ROMAN | SHISHIR 925.384.1196 | 2020-10-27 | 0 | 2020-10-26 12:48 |  | PENDING PG&E (CONTACT INFO) |  | GC |  | 2020-10-26 | POST | 35057374-R9R0-19380 | PROPIPE | 3025 MONTICELLO DR | Stockton | STOCKTON | 1 |  | Need CA to access Foundation CO, Wall CO or Roof Vent. Lower CO is buried | [10 empty] | - @DIVISION/CITY: STOCKTON / StocktonGC // POST 35057374-R9R0-193803025 MONTICELLO DR, StocktonCUSTOMER: NOTE: Need CA to access Foundation CO, Wall CO or Roof Vent. Lower CO is buriedQC: SHISHIR 925.384.1196DUE DATE: 10/27/20:: |  | 2020-10-27 10:27 | 3025 MONTICELLO DR | STOCKTON |  |  | 2020-10-28 | [11 empty] | - @StocktonCONFIRMATION: 35057374-R9R0-19380TYPE: POST3025 MONTICELLO DR, StocktonCUSTOMER: NOTE: Need CA to access Foundation CO, Wall CO or Roof Vent. Lower CO is buried
CUSTOMER ACCESS | DAVID SALAS | PATRICK 925.384.1182 | 2020-10-28 | 1 | 2020-10-23 14:19 |  | PENDING PG&E (CONTACT INFO) |  | COPPER |  | 2020-10-23 | POST | 35156931-JH3N-19466 | PROPIPE | 502 W ORANGEBURG AVE | MODESTO | YOSEMITE | 1 |  | ROOTS IN TAP. CANNOT LAUNCH. NEED PUSH FROM CO IN BACKYARD. | [10 empty] | - @DIVISION/CITY: YOSEMITE / MODESTOCOPPER // POST 35156931-JH3N-19466502 W ORANGEBURG AVE, MODESTOCUSTOMER: NOTE: ROOTS IN TAP. CANNOT LAUNCH. NEED PUSH FROM CO IN BACKYARD.QC: PATRICK 925.384.1182DUE DATE: 10/28/20:: |  | 2020-10-27 10:27 | 502 W ORANGEBURG AVE | MODESTO |  |  | 2020-10-28 | [11 empty] | - @MODESTOCONFIRMATION: 35156931-JH3N-19466TYPE: POST502 W ORANGEBURG AVE, MODESTOCUSTOMER: NOTE: ROOTS IN TAP. CANNOT LAUNCH. NEED PUSH FROM CO IN BACKYARD.
JETTING | DAVID SALAS | PATRICK 925.384.1182 | 2020-10-14 | -13 | 2020-10-23 09:36 |  | Past Due |  | COPPER | 2020-10-23 | 2020-10-23 | PRE | 35153893-DHSO-19340 | PROPIPE | 677 LAUREL AVE | MENLO PARK | PENINSULA | 1 | CHANG,WAN - Cellular Phone: (415) 999-5156 | JET DEBRIS BLOCKING MAIN LEADING TO PL677. IF NECESSARY, JET BEYOND PL677 TO LATERAL TO CLEAR LONGSIDE. |  |  | 10/23/20 DG LVM | 10/26/20 DG LVM | [6 empty] | - @DIVISION/CITY: PENINSULA / MENLO PARKCOPPER // PRE 35153893-DHSO-19340677 LAUREL AVE, MENLO PARKCUSTOMER: CHANG,WAN - Cellular Phone: (415) 999-5156NOTE: JET DEBRIS BLOCKING MAIN LEADING TO PL677. IF NECESSARY, JET BEYOND PL677 TO LATERAL TO CLEAR LONGSIDE.QC: PATRICK 925.384.1182DUE DATE: 10/14/20:: |  | 2020-10-27 10:27 | 677 LAUREL AVE | MENLO PARK |  |  | 2020-10-28 | [11 empty] | - @MENLO PARKCONFIRMATION: 35153893-DHSO-19340TYPE: PRE677 LAUREL AVE, MENLO PARKCUSTOMER: CHANG,WAN - Cellular Phone: (415) 999-5156NOTE: JET DEBRIS BLOCKING MAIN LEADING TO PL677. IF NECESSARY, JET BEYOND PL677 TO LATERAL TO CLEAR LONGSIDE. |  |  |  | 1-2 HOURS | MH668 | PL677
CUSTOMER ACCESS | DAVID SALAS | PATRICK 925.384.1182 | 2020-10-21 | -6 | 2020-10-22 15:17 | Tuesday, 10/27/20 - @8-10DIVISION/CITY: DE ANZA / SUNNYVALECOPPER // PRE 35153820-DHSO-17252745 S BERNARDO AVE, SUNNYVALECUSTOMER: CITRA PROPERTY OWNER LLC - Business Phone - Primary: (408) 245-9700NOTE: NEED ACCESS TO CLEANOUTS IN BUILDINGS ACROSS FROM PARKING STALLS TO CLEAR LATERALS DG THE MAINT SUP. WILL SHOW YOU WHERE CO ARE THEY ARE PUTTING NOTICE TO TENANTS NOT TO PARK THERE.QC: PATRICK 925.384.1182DUE DATE: 10/21/20:: | Appt Created |  | COPPER | 2020-10-23 | 2020-10-22 | PRE | 35153820-DHSO-17252 | PROPIPE | 745 S BERNARDO AVE | SUNNYVALE | DE ANZA | 1 | CITRA PROPERTY OWNER LLC - Business Phone - Primary: (408) 245-9700 | NEED ACCESS TO CLEANOUTS IN BUILDINGS ACROSS FROM PARKING STALLS TO CLEAR LATERALS DG THE MAINT SUP. WILL SHOW YOU WHERE CO ARE THEY ARE PUTTING NOTICE TO TENANTS NOT TO PARK THERE. |  |  | 10/23/20 DG SET APT |  |  |  |  | 2020-10-27 | 8-10 | Tuesday, 10/27/20 | Tuesday, 10/27/20 - @8-10DIVISION/CITY: DE ANZA / SUNNYVALECOPPER // PRE 35153820-DHSO-17252745 S BERNARDO AVE, SUNNYVALECUSTOMER: CITRA PROPERTY OWNER LLC - Business Phone - Primary: (408) 245-9700NOTE: NEED ACCESS TO CLEANOUTS IN BUILDINGS ACROSS FROM PARKING STALLS TO CLEAR LATERALS DG THE MAINT SUP. WILL SHOW YOU WHERE CO ARE THEY ARE PUTTING NOTICE TO TENANTS NOT TO PARK THERE.QC: PATRICK 925.384.1182DUE DATE: 10/21/20:: |  | 2020-10-27 10:27 | 745 S BERNARDO AVE | SUNNYVALE |  |  | 2020-10-28 | [11 empty] | Tuesday, 10/27/20 - @8-10SUNNYVALECONFIRMATION: 35153820-DHSO-17252TYPE: PRE745 S BERNARDO AVE, SUNNYVALECUSTOMER: CITRA PROPERTY OWNER LLC - Business Phone - Primary: (408) 245-9700NOTE: NEED ACCESS TO CLEANOUTS IN BUILDINGS ACROSS FROM PARKING STALLS TO CLEAR LATERALS DG THE MAINT SUP. WILL SHOW YOU WHERE CO ARE THEY ARE PUTTING NOTICE TO TENANTS NOT TO PARK THERE.
CUSTOMER ACCESS | DAVID SALAS | PATRICK 925.384.1182 | 2020-10-27 | 0 | 2020-10-21 15:36 |  | Past Due |  | COPPER | 2020-10-23 | 2020-10-21 | PRE | 35155932-DHSO-19422 | PROPIPE | 182 OAKDALE AVE | MILL VALLEY | NORTH BAY | 1 | ROBERTSON,STEPHANIE - Home Phone - Primary: (415) 876-6719, Business 650-825-2291, Business Secondary 415-518-5733 | NEED TO LOOK FOR CO FOR ACCESS TO L3 AND L4 |  |  | 10/23/20 DG LVM | 10/26/20 DG *6719 DXD *2291 FAST BUSY LVM | [6 empty] | - @DIVISION/CITY: NORTH BAY / MILL VALLEYCOPPER // PRE 35155932-DHSO-19422182 OAKDALE AVE, MILL VALLEYCUSTOMER: ROBERTSON,STEPHANIE - Home Phone - Primary: (415) 876-6719, Business 650-825-2291, Business Secondary 415-518-5733NOTE: NEED TO LOOK FOR CO FOR ACCESS TO L3 AND L4QC: PATRICK 925.384.1182DUE DATE: 10/27/20:: |  | 2020-10-27 10:27 | 182 OAKDALE AVE | MILL VALLEY |  |  | 2020-10-28 | [11 empty] | - @MILL VALLEYCONFIRMATION: 35155932-DHSO-19422TYPE: PRE182 OAKDALE AVE, MILL VALLEYCUSTOMER: ROBERTSON,STEPHANIE - Home Phone - Primary: (415) 876-6719, Business 650-825-2291, Business Secondary 415-518-5733NOTE: NEED TO LOOK FOR CO FOR ACCESS TO L3 AND L4
CUSTOMER ACCESS | ALMA JIMENEZ | SHISHIR 925.384.1196 | 2020-10-02 | -25 | 2020-10-21 13:41 |  | PENDING PG&E (CONTACT INFO) |  | GC |  | 2020-10-21 | PRE | 31486340-A2JI-17663 | PROPIPE | 3164 BONA ST | OAKLAND | EAST BAY | 1 |  | Need Access to clear the lateral | [10 empty] | - @DIVISION/CITY: EAST BAY / OAKLANDGC // PRE 31486340-A2JI-176633164 BONA ST, OAKLANDCUSTOMER: NOTE: Need Access to clear the lateralQC: SHISHIR 925.384.1196DUE DATE: 10/02/20:: |  | 2020-10-27 10:27 | 3164 BONA ST | OAKLAND |  |  | 2020-10-28 | [11 empty] | - @OAKLANDCONFIRMATION: 31486340-A2JI-17663TYPE: PRE3164 BONA ST, OAKLANDCUSTOMER: NOTE: Need Access to clear the lateral
CUSTOMER ACCESS | DAVID SALAS | PATRICK 925.384.1182 | 2020-10-27 | 0 | 2020-10-21 11:04 |  | PENDING PG&E (SENT BACK) |  | COPPER | 2020-10-23 | 2020-10-21 | POST | 35207886-DHSO-19500 | PROPIPE | 2811 CHERRY ST | BERKELEY | EAST BAY | 1 | LEAVER,MICHAEL - Home Phone - Primary: (510) 548-1724, Business 510-540-4447 Secondary Contact: ENGELHART,PETER Home 510-845-5061 Owner is Michael Leaver WIFE 510.368.5226 | GATE IN BACKYARD. VERIFY BACK STRUCTURE. | 44362083-DHSO-19423 OLD # |  | 10/23/20 DG *1724 DXD | 10/23/20 DG LVM *5061 | 10/26/20 DG LVM | N | 2020-10-23 |  |  |  | - @DIVISION/CITY: EAST BAY / BERKELEYCOPPER // POST 35207886-DHSO-195002811 CHERRY ST, BERKELEYCUSTOMER: LEAVER,MICHAEL - Home Phone - Primary: (510) 548-1724, Business 510-540-4447 Secondary Contact: ENGELHART,PETER Home 510-845-5061 Owner is Michael Leaver WIFE 510.368.5226NOTE: GATE IN BACKYARD. VERIFY BACK STRUCTURE.QC: PATRICK 925.384.1182DUE DATE: 10/27/20:: |  | 2020-10-27 10:27 | 2811 CHERRY ST | BERKELEY |  |  | 2020-10-28 | [11 empty] | - @BERKELEYCONFIRMATION: 35207886-DHSO-19500TYPE: POST2811 CHERRY ST, BERKELEYCUSTOMER: LEAVER,MICHAEL - Home Phone - Primary: (510) 548-1724, Business 510-540-4447 Secondary Contact: ENGELHART,PETER Home 510-845-5061 Owner is Michael Leaver WIFE 510.368.5226NOTE: GATE IN BACKYARD. VERIFY BACK STRUCTURE.
JETTING | DAVID SALAS | RAFAEL 949.427.3838 | 2020-10-05 | -22 | 2020-10-20 13:38 | Monday, 10/26/20 - @8-10DIVISION/CITY: NORTH BAY / Mill ValleyCSR/ACCUBORE // PRE 35155951-MIBX-19267307 TENNESSEE AVE, Mill ValleyCUSTOMER: WHITNEY,LEWIS – Cellular Phone: (415) 308-0711 Business Phone - Primary (415) 229-8899 IVAN 415.699.0176 CARE TAKERNOTE: Need to clean both laterals for address 307 Tennessee Ave. NEED TO JET THE LINE FOUNDATION TO MAIN. DG CUSTOMER IS OUT OF THE COUNTRY HE WILL HAVE SOMEONE BRING DOG INSIDE AND UNLOCK GATES FROM 8-10QC: RAFAEL 949.427.3838DUE DATE: 10/05/20:: | Appt Created |  | CSR/ACCUBORE | 2020-10-21 | 2020-10-20 | PRE | 35155951-MIBX-19267 | PROPIPE | 307 TENNESSEE AVE | Mill Valley | NORTH BAY | 1 | WHITNEY,LEWIS – Cellular Phone: (415) 308-0711 Business Phone - Primary (415) 229-8899 IVAN 415.699.0176 CARE TAKER | Need to clean both laterals for address 307 Tennessee Ave. NEED TO JET THE LINE FOUNDATION TO MAIN. DG CUSTOMER IS OUT OF THE COUNTRY HE WILL HAVE SOMEONE BRING DOG INSIDE AND UNLOCK GATES FROM 8-10 |  |  | 10/21/20 DG LVM | 10/21/20 DG SET APT |  |  |  | 2020-10-26 | 8-10 | Monday, 10/26/20 | Monday, 10/26/20 - @8-10DIVISION/CITY: NORTH BAY / Mill ValleyCSR/ACCUBORE // PRE 35155951-MIBX-19267307 TENNESSEE AVE, Mill ValleyCUSTOMER: WHITNEY,LEWIS – Cellular Phone: (415) 308-0711 Business Phone - Primary (415) 229-8899 IVAN 415.699.0176 CARE TAKERNOTE: Need to clean both laterals for address 307 Tennessee Ave. NEED TO JET THE LINE FOUNDATION TO MAIN. DG CUSTOMER IS OUT OF THE COUNTRY HE WILL HAVE SOMEONE BRING DOG INSIDE AND UNLOCK GATES FROM 8-10QC: RAFAEL 949.427.3838DUE DATE: 10/05/20:: |  | 2020-10-27 10:27 | 307 TENNESSEE AVE | MILL VALLEY |  |  | 2020-10-28 | [11 empty] | Monday, 10/26/20 - @8-10Mill ValleyCONFIRMATION: 35155951-MIBX-19267TYPE: PRE307 TENNESSEE AVE, Mill ValleyCUSTOMER: WHITNEY,LEWIS – Cellular Phone: (415) 308-0711 Business Phone - Primary (415) 229-8899 IVAN 415.699.0176 CARE TAKERNOTE: Need to clean both laterals for address 307 Tennessee Ave. NEED TO JET THE LINE FOUNDATION TO MAIN. DG CUSTOMER IS OUT OF THE COUNTRY HE WILL HAVE SOMEONE BRING DOG INSIDE AND UNLOCK GATES FROM 8-10 |  |  |  | 2 hours | Foundation cleanouts | Main
CUSTOMER ACCESS | DAVID SALAS | ERIC 925.526.4463 | 2020-10-15 | -12 | 2020-10-20 11:35 |  | C/A Done | NN | COPPER | 2020-10-21 | 2020-10-20 | PRE | 35156945-DHSO-19349 | PROPIPE | 831 8TH AVE | REDWOOD CITY | PENINSULA | 1 | MORRIS,CARRIE – Home Phone - Primary: (650) 365-4834 Cellular Phone (650) 333-5492 Cellular Phone (650) 796-9917 | Customer refused roof access during appointment. DG SPOKE W/CARRIE SHE SAID HER HUSBAND DID NOT WANT US ON THE ROOF. HE ALSO SAID THAT THEY WERE NOT INFORMED ABOUT ANY WORK BEING DONE. |  |  | 10/21/20 DG SPOKE REFUSED. |  |  | N | 2020-10-21 |  |  |  | - @DIVISION/CITY: PENINSULA / REDWOOD CITYCOPPER // PRE 35156945-DHSO-19349831 8TH AVE, REDWOOD CITYCUSTOMER: MORRIS,CARRIE – Home Phone - Primary: (650) 365-4834 Cellular Phone (650) 333-5492 Cellular Phone (650) 796-9917NOTE: Customer refused roof access during appointment. DG SPOKE W/CARRIE SHE SAID HER HUSBAND DID NOT WANT US ON THE ROOF. HE ALSO SAID THAT THEY WERE NOT INFORMED ABOUT ANY WORK BEING DONE.QC: ERIC 925.526.4463DUE DATE: 10/15/20:: |  | 2020-10-27 10:27 | 831 8TH AVE | REDWOOD CITY |  |  | 2020-10-28 | [11 empty] | - @REDWOOD CITYCONFIRMATION: 35156945-DHSO-19349TYPE: PRE831 8TH AVE, REDWOOD CITYCUSTOMER: MORRIS,CARRIE – Home Phone - Primary: (650) 365-4834 Cellular Phone (650) 333-5492 Cellular Phone (650) 796-9917NOTE: Customer refused roof access during appointment. DG SPOKE W/CARRIE SHE SAID HER HUSBAND DID NOT WANT US ON THE ROOF. HE ALSO SAID THAT THEY WERE NOT INFORMED ABOUT ANY WORK BEING DONE. | [6 empty] | TRUE | TRUE
CUSTOMER ACCESS | ROBERTO ROMAN | ERIC 925.526.4463 | 2020-10-23 | -4 | 2020-10-19 12:05 |  | Past Due |  | COPPER | 2020-10-23 | 2020-10-19 | PRE | 35156205-R9R0-19255 | PROPIPE | 59 RANDOLPH AVE | SOUTH SAN FRANCISCO | PENINSULA | 1 | SULLIVAN,MARY - Home Phone - Primary: (650) 273-1298, Alternate 650-273-1224 | Need access to rear. |  |  | 10/23/20 * 1298 FAST BUSY *1224 CANT LVM | 10/26/20 DG CANT LVM | [6 empty] | - @DIVISION/CITY: PENINSULA / SOUTH SAN FRANCISCOCOPPER // PRE 35156205-R9R0-1925559 RANDOLPH AVE, SOUTH SAN FRANCISCOCUSTOMER: SULLIVAN,MARY - Home Phone - Primary: (650) 273-1298, Alternate 650-273-1224NOTE: Need access to rear.QC: ERIC 925.526.4463DUE DATE: 10/23/20:: |  | 2020-10-27 10:27 | 59 RANDOLPH AVE | SOUTH SAN FRANCISCO |  |  | 2020-10-28 | [11 empty] | - @SOUTH SAN FRANCISCOCONFIRMATION: 35156205-R9R0-19255TYPE: PRE59 RANDOLPH AVE, SOUTH SAN FRANCISCOCUSTOMER: SULLIVAN,MARY - Home Phone - Primary: (650) 273-1298, Alternate 650-273-1224NOTE: Need access to rear.
CUSTOMER ACCESS | DAVID SALAS | ERIC 925.526.4463 | 2020-10-20 | -7 | 2020-10-19 12:03 | Thursday, 10/22/20 - @8-10DIVISION/CITY: DIABLO / ALAMOCOPPER // POST 35153650-DHSO-1939180 VIA ROBLES, ALAMOCUSTOMER: SURYADEVARA,JAYASREE - Home Phone - Primary: (925) 938-3056, Cell (626) 319-3946NOTE: Had access on PRE, need it again for POST DG SPOKE W/JAY HE WILL BE HOME TO ALLOW ACCESS PLEASE COME AS EARLY AS POSSIBLE.QC: ERIC 925.526.4463DUE DATE: 10/20/20:: | Appt Created |  | COPPER | 2020-10-20 | 2020-10-19 | POST | 35153650-DHSO-19391 | PROPIPE | 80 VIA ROBLES | ALAMO | DIABLO | 1 | SURYADEVARA,JAYASREE - Home Phone - Primary: (925) 938-3056, Cell (626) 319-3946 | Had access on PRE, need it again for POST DG SPOKE W/JAY HE WILL BE HOME TO ALLOW ACCESS PLEASE COME AS EARLY AS POSSIBLE. |  |  | 10/20/20 DG LVM | 10/21/20 DG SET APT |  |  |  | 2020-10-22 | 8-10 | Thursday, 10/22/20 | Thursday, 10/22/20 - @8-10DIVISION/CITY: DIABLO / ALAMOCOPPER // POST 35153650-DHSO-1939180 VIA ROBLES, ALAMOCUSTOMER: SURYADEVARA,JAYASREE - Home Phone - Primary: (925) 938-3056, Cell (626) 319-3946NOTE: Had access on PRE, need it again for POST DG SPOKE W/JAY HE WILL BE HOME TO ALLOW ACCESS PLEASE COME AS EARLY AS POSSIBLE.QC: ERIC 925.526.4463DUE DATE: 10/20/20:: |  | 2020-10-27 10:27 | 80 VIA ROBLES | ALAMO |  |  | 2020-10-28 | [11 empty] | Thursday, 10/22/20 - @8-10ALAMOCONFIRMATION: 35153650-DHSO-19391TYPE: POST80 VIA ROBLES, ALAMOCUSTOMER: SURYADEVARA,JAYASREE - Home Phone - Primary: (925) 938-3056, Cell (626) 319-3946NOTE: Had access on PRE, need it again for POST DG SPOKE W/JAY HE WILL BE HOME TO ALLOW ACCESS PLEASE COME AS EARLY AS POSSIBLE.
CUSTOMER ACCESS | ALMA JIMENEZ | SHISHIR 925.384.1196 | 2020-10-23 | -4 | 2020-10-19 09:58 |  | C/A Done | NN | GC | 2020-10-21 | 2020-10-19 | PRE | 31486340-A2JI-19125 | PROPIPE | 3218 BONA ST | OAKLAND | EAST BAY | 1 | CORONA,RUBEN (510) 708-0331 | Need CA to clear the lateral. No Taps on Mainline. Probably wye to 3224 Bona St. |  |  | 10/21/20 DG LVM | 10/22/20 DG LVM | 10/23/20 DG LVM | [5 empty] | - @DIVISION/CITY: EAST BAY / OAKLANDGC // PRE 31486340-A2JI-191253218 BONA ST, OAKLANDCUSTOMER: CORONA,RUBEN (510) 708-0331NOTE: Need CA to clear the lateral. No Taps on Mainline. Probably wye to 3224 Bona St.QC: SHISHIR 925.384.1196DUE DATE: 10/23/20:: |  | 2020-10-27 10:27 | 3218 BONA ST | OAKLAND |  |  | 2020-10-28 | [11 empty] | - @OAKLANDCONFIRMATION: 31486340-A2JI-19125TYPE: PRE3218 BONA ST, OAKLANDCUSTOMER: CORONA,RUBEN (510) 708-0331NOTE: Need CA to clear the lateral. No Taps on Mainline. Probably wye to 3224 Bona St. | [6 empty] | TRUE | TRUE
JETTING | DAVID SALAS | PATRICK 925.384.1182 | 2020-10-14 | -13 | 2020-10-19 09:29 | Wednesday, 10/21/20 - @10-12DIVISION/CITY: PENINSULA / MENLO PARKCOPPER // PRE 35153893-DHSO-19340668 LAUREL AVE, MENLO PARKCUSTOMER: ERIC SEIDEL CELL: 713-385-4340NOTE: DEBRIS BLOCKING/CAMERA UNDER WATER. CLEAR TO PL OF LONG SIDE. DG SPOKE W/ERIC HE WILL BE HOME TO ALLOW ACCESS TO THE BACK YARD.QC: PATRICK 925.384.1182DUE DATE: 10/14/20:: | Appt Created |  | COPPER | 2020-10-19 | 2020-10-19 | PRE | 35153893-DHSO-19340 | PROPIPE | 668 LAUREL AVE | MENLO PARK | PENINSULA | 1 | ERIC SEIDEL CELL: 713-385-4340 | DEBRIS BLOCKING/CAMERA UNDER WATER. CLEAR TO PL OF LONG SIDE. DG SPOKE W/ERIC HE WILL BE HOME TO ALLOW ACCESS TO THE BACK YARD. |  |  | 10/19/20 DG SET APT |  |  |  |  | 2020-10-21 | 10-12 | Wednesday, 10/21/20 | Wednesday, 10/21/20 - @10-12DIVISION/CITY: PENINSULA / MENLO PARKCOPPER // PRE 35153893-DHSO-19340668 LAUREL AVE, MENLO PARKCUSTOMER: ERIC SEIDEL CELL: 713-385-4340NOTE: DEBRIS BLOCKING/CAMERA UNDER WATER. CLEAR TO PL OF LONG SIDE. DG SPOKE W/ERIC HE WILL BE HOME TO ALLOW ACCESS TO THE BACK YARD.QC: PATRICK 925.384.1182DUE DATE: 10/14/20:: |  | 2020-10-27 10:27 | 668 LAUREL AVE | MENLO PARK |  |  | 2020-10-28 | [11 empty] | Wednesday, 10/21/20 - @10-12MENLO PARKCONFIRMATION: 35153893-DHSO-19340TYPE: PRE668 LAUREL AVE, MENLO PARKCUSTOMER: ERIC SEIDEL CELL: 713-385-4340NOTE: DEBRIS BLOCKING/CAMERA UNDER WATER. CLEAR TO PL OF LONG SIDE. DG SPOKE W/ERIC HE WILL BE HOME TO ALLOW ACCESS TO THE BACK YARD. |  |  |  | 1-2 HOURS | MH668 | PL677
CUSTOMER ACCESS | MICHAEL STEELE | RAFAEL 949.427.3838 | 2020-10-22 | -5 | 2020-10-16 16:57 | Thursday, 10/29/20 - @10-12DIVISION/CITY: NORTH VALLEY / PARADISEGC // PRE 31488645-MFSR-194176154 TYRAN WAY, PARADISECUSTOMER: ROZYCKI,JERRY – Home Phone - Primary: (530) 520-4586 Alternate Contact Phone (530) 413-1083NOTE: Need to push to septic. 1st door tag DG JERRY WILL BE HOME TO ALLOW ACCESS TO THE BACK YARD WHERE SEPTIC IS.QC: RAFAEL 949.427.3838DUE DATE: 10/22/20:: | Appt Created |  | GC | 2020-10-27 | 2020-10-19 | PRE | 31488645-MFSR-19417 | PROPIPE | 6154 TYRAN WAY | PARADISE | NORTH VALLEY | 1 | ROZYCKI,JERRY – Home Phone - Primary: (530) 520-4586 Alternate Contact Phone (530) 413-1083 | Need to push to septic. 1st door tag DG JERRY WILL BE HOME TO ALLOW ACCESS TO THE BACK YARD WHERE SEPTIC IS. |  |  | 10/27/20 DG SET APT |  |  |  |  | 2020-10-29 | 10-12 | Thursday, 10/29/20 | Thursday, 10/29/20 - @10-12DIVISION/CITY: NORTH VALLEY / PARADISEGC // PRE 31488645-MFSR-194176154 TYRAN WAY, PARADISECUSTOMER: ROZYCKI,JERRY – Home Phone - Primary: (530) 520-4586 Alternate Contact Phone (530) 413-1083NOTE: Need to push to septic. 1st door tag DG JERRY WILL BE HOME TO ALLOW ACCESS TO THE BACK YARD WHERE SEPTIC IS.QC: RAFAEL 949.427.3838DUE DATE: 10/22/20:: |  | 2020-10-27 10:27 | 6154 TYRAN WAY | PARADISE |  |  | 2020-10-28 | [11 empty] | Thursday, 10/29/20 - @10-12PARADISECONFIRMATION: 31488645-MFSR-19417TYPE: PRE6154 TYRAN WAY, PARADISECUSTOMER: ROZYCKI,JERRY – Home Phone - Primary: (530) 520-4586 Alternate Contact Phone (530) 413-1083NOTE: Need to push to septic. 1st door tag DG JERRY WILL BE HOME TO ALLOW ACCESS TO THE BACK YARD WHERE SEPTIC IS.
CUSTOMER ACCESS | DAVID SALAS | RAFAEL 949.427.3838 | 2020-10-05 | -22 | 2020-10-16 14:58 | Wednesday, 10/21/20 - @2-4DIVISION/CITY: PENINSULA / SOUTH SAN FRANCISCOCSR/ACCUBORE // PRE 35156201-R9R0-19252254 GRAND AVE, SOUTH SAN FRANCISCOCUSTOMER: SANDOVAL,YULEYMA Business Phone - Primary (650) 834-2835NOTE: Sewer main in easement DG YULEYMA SHE WILL BE HOME TO GRANT ACCESS 2-4 WED REAR IS OPEN FRONT IS LOCKED.QC: RAFAEL 949.427.3838DUE DATE: 10/05/20:: | Appt Created |  | CSR/ACCUBORE | 2020-10-19 | 2020-10-16 | PRE | 35156201-R9R0-19252 | PROPIPE | 254 GRAND AVE | SOUTH SAN FRANCISCO | PENINSULA | 1 | SANDOVAL,YULEYMA Business Phone - Primary (650) 834-2835 | Sewer main in easement DG YULEYMA SHE WILL BE HOME TO GRANT ACCESS 2-4 WED REAR IS OPEN FRONT IS LOCKED. |  |  | 10/19/20 DG LVM | 10/19/20 DG SET APT |  |  |  | 2020-10-21 | 2-4 | Wednesday, 10/21/20 | Wednesday, 10/21/20 - @2-4DIVISION/CITY: PENINSULA / SOUTH SAN FRANCISCOCSR/ACCUBORE // PRE 35156201-R9R0-19252254 GRAND AVE, SOUTH SAN FRANCISCOCUSTOMER: SANDOVAL,YULEYMA Business Phone - Primary (650) 834-2835NOTE: Sewer main in easement DG YULEYMA SHE WILL BE HOME TO GRANT ACCESS 2-4 WED REAR IS OPEN FRONT IS LOCKED.QC: RAFAEL 949.427.3838DUE DATE: 10/05/20:: |  | 2020-10-27 10:27 | 254 GRAND AVE | SOUTH SAN FRANCISCO |  |  | 2020-10-28 | [11 empty] | Wednesday, 10/21/20 - @2-4SOUTH SAN FRANCISCOCONFIRMATION: 35156201-R9R0-19252TYPE: PRE254 GRAND AVE, SOUTH SAN FRANCISCOCUSTOMER: SANDOVAL,YULEYMA Business Phone - Primary (650) 834-2835NOTE: Sewer main in easement DG YULEYMA SHE WILL BE HOME TO GRANT ACCESS 2-4 WED REAR IS OPEN FRONT IS LOCKED.
CUSTOMER ACCESS | DAVID SALAS | RAFAEL 949.427.3838 | 2020-10-05 | -22 | 2020-10-16 14:57 | Friday, 10/23/20 - @10:30-12DIVISION/CITY: PENINSULA / SOUTH SAN FRANCISCOCSR/ACCUBORE // PRE 35156201-R9R0-19252250 GRAND AVE, SOUTH SAN FRANCISCOCUSTOMER: WINNIE FONG – Business Phone - Primary: (650) 873-6787NOTE: Sewer main in easement DG SPOKE W/CUSTOMER WILL LET OWNER KNOW WE CAN COME AFTER 10:30.QC: RAFAEL 949.427.3838DUE DATE: 10/05/20:: | Appt Created |  | CSR/ACCUBORE | 2020-10-19 | 2020-10-16 | PRE | 35156201-R9R0-19252 | PROPIPE | 250 GRAND AVE | SOUTH SAN FRANCISCO | PENINSULA | 1 | WINNIE FONG – Business Phone - Primary: (650) 873-6787 | Sewer main in easement DG SPOKE W/CUSTOMER WILL LET OWNER KNOW WE CAN COME AFTER 10:30. |  |  | 10/19/20 DG LVM | 10/20/20 DG SET APT |  |  |  | 2020-10-23 | 10:30-12 | Friday, 10/23/20 | Friday, 10/23/20 - @10:30-12DIVISION/CITY: PENINSULA / SOUTH SAN FRANCISCOCSR/ACCUBORE // PRE 35156201-R9R0-19252250 GRAND AVE, SOUTH SAN FRANCISCOCUSTOMER: WINNIE FONG – Business Phone - Primary: (650) 873-6787NOTE: Sewer main in easement DG SPOKE W/CUSTOMER WILL LET OWNER KNOW WE CAN COME AFTER 10:30.QC: RAFAEL 949.427.3838DUE DATE: 10/05/20:: |  | 2020-10-27 10:27 | 250 GRAND AVE | SOUTH SAN FRANCISCO |  |  | 2020-10-28 | [11 empty] | Friday, 10/23/20 - @10:30-12SOUTH SAN FRANCISCOCONFIRMATION: 35156201-R9R0-19252TYPE: PRE250 GRAND AVE, SOUTH SAN FRANCISCOCUSTOMER: WINNIE FONG – Business Phone - Primary: (650) 873-6787NOTE: Sewer main in easement DG SPOKE W/CUSTOMER WILL LET OWNER KNOW WE CAN COME AFTER 10:30.
CUSTOMER ACCESS | DAVID SALAS | PATRICK 925.384.1182 | 2020-10-20 | -7 | 2020-10-16 14:21 |  | C/A Done | NN | COPPER | 2020-10-19 | 2020-10-16 | PRE | 35153970-DHSO-19394 | PROPIPE | 1301 COLUMBUS AVE | BURLINGAME | PENINSULA | 1 | LOWRIE,J W - Home Phone - Primary: (650) 344-6125 | POSSIBLE EASMENT NEED ANOTHER CA APPT FIRST THING IN THE MORNING. CUSTOMER LEFT FOR WORK RIGHT WHEN OPERATOR GOT THERE. |  |  | 10/19/20 DG LVM | 10/23/20 DG LVM | 10/26/20 DG LVM | Y | 2020-10-26 |  |  |  | - @DIVISION/CITY: PENINSULA / BURLINGAMECOPPER // PRE 35153970-DHSO-193941301 COLUMBUS AVE, BURLINGAMECUSTOMER: LOWRIE,J W - Home Phone - Primary: (650) 344-6125NOTE: POSSIBLE EASMENT NEED ANOTHER CA APPT FIRST THING IN THE MORNING. CUSTOMER LEFT FOR WORK RIGHT WHEN OPERATOR GOT THERE.QC: PATRICK 925.384.1182DUE DATE: 10/20/20:: |  | 2020-10-27 10:27 | 1301 COLUMBUS AVE | BURLINGAME |  |  | 2020-10-28 | [11 empty] | - @BURLINGAMECONFIRMATION: 35153970-DHSO-19394TYPE: PRE1301 COLUMBUS AVE, BURLINGAMECUSTOMER: LOWRIE,J W - Home Phone - Primary: (650) 344-6125NOTE: POSSIBLE EASMENT NEED ANOTHER CA APPT FIRST THING IN THE MORNING. CUSTOMER LEFT FOR WORK RIGHT WHEN OPERATOR GOT THERE. | [6 empty] | TRUE | TRUE

## Comments
Row 2790 | @cody.dorrell@pro-pipe.com Emily requested i get this one - still needed, correct? jayme | Jayme Gordis | 05/09/19 1:51 PM